## Sheet1
Status Dated on 3rd April 23
Sr No. | Task Detail | Status | Priority | Allocated To
1 | Maintaining the analysis and docs for the requirement Release and Update the different versons of application.. Supports and fixes Working on Optimization .. | Prepared and shared for discussion In Progress Doing support fixes and Interviews |  | Ravishankar
2 | 16.0 CREATE NEW UI TO CHANGE THE THREAD AVERAGE BY IE TEAM TILL CUT 99% | Done(Pending to live) | 5 | Girish
3 | 18.2 In the Wastage Popup need to show the different stage difference quantity in reverse order… | Done(Pending to live) | 7 | Rajeev
4 | 18.4 Apply the Edit Range of the Cut Wastage in wastage pop up from order cut wastage to costing cut wastage Need to implement in all dependent sp and functions and have to test thorough | Done(Pending to live) | 8 | Rajeev
5 | Stock Migration for stock summary Report | Done (Final round of reconcillation) |  | Girish
6 | For fabric and accessory Internal challan need to allow GST number entry | In Final Testing |  | Girish
7 | Required Quantity for Fabric in Four-point check if extra quantity is there based on PO to decide the use of extra stock | In Final Testing
8 | Required Quantity for Accessory in Four-point check if extra quantity is there based on PO to decide the use of extra stock | In Final Testing
9 | External challan --> sampling checkbox to enter supplier name. | Done(Pending to live)
10 | Raise and revise PO sorting. Based on latest po on top | Done(Pending to live)
11 | In fabric Four-point check claimed quantity freezed by default. | Done(Pending to live)
12 | In accessory and fabric Four-point check claimed quantity freezed by default. | Done(Pending to live)
13 | Returned Quantity in Internal challan. Accessory | In Testing
14 | Different Scenerio Testing for the cut Wastage implementation Approximately 12 scenerios to test by different combination of stage selection and the complete flow in cluding allocations stock movement and reutilisation logics. | In Testing
15 | Critical Path Report Updates | In Progress |  | Girish
16 | Cut average change and archive moved contracts handling even po not closed | In Progress |  | Girish
17 | Rates Excel updates and modification | In Queue |  | Girish
18 | Cut Wastage update history | In Progress
19 | quotation pop up in raise and revise po should have the last po details as well. | In Progress | 10 | Rajeev
20 | Need to work on split implementation refinement and correction | In Progress |  | Girish and RSB
21 | In the Core Report Body the profit comparision Report Mock up done Modification of Core Report for Costed and Actual Material Cost | In Queue |  | Rajeev
22 | Sampling and Scrap Challan for Fabric and Accessory Mock up creation need to discuss with hemant sir | In Queue |  | Girish
23 | Daily stock movement and stock summary excel for accessory | In Queue |  | Girish
24 | Need to allow the colour change of fabric till bulk approval done or stage srv received. If anyone of them is done then color change not allowed If colour changed then task need to be created for PO Update | In Queue |  | Girish
25 | Testing on new server the complete application | In Queue
26 | Need to proceed to run, Order for shahi as before ERP migration. 1) Now we will create the Sahi Fabric and Sahi Accessory in system and after completion of orders these qualities may be dissabled 2) Need to raise the Internal from newly created supplier Sahi_Temp and this will be excluded from all the reports of the material. | Conclusion
27 | New Server complete application testing and move in the cloud
28 | Quantity shifting from one contract to other allocation logic Working for fabric and accessory working on the logic of quantity movement after the UI. | Need to Final test and Update in Menu
29 | Separate task for sample fabric requesting | To Do
30 | New Report of the finishing superwiser need to created need to add data in the qc pop up | Indiscussion |  | Padam
31 | As discussed the report analysing the further reports | In Progress
32 | Task related tuning and fixing | To Do |  | Whole Team
33 | Material Detail Profit Loss Report analysis detailing | To Do |  | Ravishankar
34 | i) QA of all the release and Support | In Progress |  | Vaibhav
35 | Issue fixing related to the ETA and other sections for Accessory | In Progress |  | Shubhendu
36 | 1)As few of the wastage and shrinkage are get updated at the time of PO raise so there may be some difference in required quantity in quotation. We will manage the raised PO quantity subtracted too. 2) So based on admin defined shrinkage and wastage required quantity will be shown here and also the raised PO quantity will be adjusted too. Following 3 figures need to show here as follows: Total Required Po Raised quantity Balance Quantity | Pending |  | Shubhendu
37 | i) Hourly Report Update for the Today CMT and Lifetime CMT Implementation ii) Work on the Backend for handling the scenerios a) Same style Multiline b) Half stitch c) Noramal in one line -- Partially done iii) Front end showing the Today CMT % and detail in Tooltip grid. iv) Excel report for the Style CMT vs Costed CMT | This will get started again this week after completing the above task… Hold
38 | Need to discuss on few points which are discussed internally with Karan , Hemant ji and team to conclude 1) required separate task for fabric lost in residual shrinkage -- No Use 2) req separate RPOCESS ORDER (FOR JOB WORK)/PURCHASE ORDER ( FOR PURCHASE) -- To Do | In Queue
39 | Few New Requirement and their analysis and doc: 1) For Fabric in different stages different GSM as we have done for C&C -- Discarded 2) Multiple Bill with one SRV may be old as well , detail discussion required. -- Discussed and Required 3) Build configuration on the new server -- In Progress | Enriching the document |  | RSB
40 | Task Creation in case of quotation after stage selection | Need to discuss
41 | Need to discuss the extra Meterage for the sampling and fit cycle in costing based on quantity. Need to have discussion with SAM sir for the idea behind this. | Need to discuss
42 | Material Reports | In Progress
43 | 1) received item need to be added in decimal in fabric | Descarded
44 | Stock report analysis and discussion | Analysis In Progress |  | RSB
45 | New Changes in MO and Ikandi website revamping | Done waiting to update |  | Pending to Angad
46 | Residual Shrinkage need to be editable on PO | Discard
47 | Landing Page redesign after login design | On Hold |  | Dinesh+ Girish
48 | 1) Need to allow adding the bill number at the time creating the srv a) Fabric and b) Accessory | On Hold |  | Shubhendu
49 | Sampling tasks get removed on costing done need to analyse and update the solution. | On Hold

## Sheet2
Old Done stuff
Sr No. | Task Detail | Status | Allocated To
1 | 1) Fabric Excel report should have Serial Numbers from srv allocation and Rate of the PO to show. | Done
2 | 1) On consequitive access of the same costing from two users need to have check on the few basic fields if changed by other team. | Done
3 | 1) Now in cut issue request and cutting issue done screen we are allowing the Outhouse Units too. This willl help to allocate the challan in external factories too. 2) We have made update for the Debit note Number as suggested by fabric and accounts team now the format would be as Financial Year/Sequence e.g. 2022-23/1 | Done | RSB and Sanjeev
4 | 1) Residual shrinkage quantity need to shift in a separate table. | Done | RSB and Sanjeev
5 | 1) Stage wise Supplier groupped PO Report in Excel Format 2) Need to implement in the mail also | Done | Sanjeev
6 | 1) Have to show the summary total in mail body for the supplier PO Mail | Done
7 | 1) For fabric Greige Shring need to be segregared in dyeing Greige shrinkage and Printing Greige Shrinkage 2) Need to implement in the Fabric quality admin 3) Need to be implemented in the Stage selection 4) Raise and Revise PO 5) Wastage shrinkage pop up 6) All Schedulaers need to be review for stock management | Done | Sanjeev
8 | 1) Update in Raise and Revise PO for search Need to provide the Color / Print specific search except first stage (without finish) 2) Manage PO Search Update Based on Quality and Supplier | Done | Sanjeev
9 | Quotation screen search based on color print too Here need to provide supplier specific search too | Done
10 | Need to work on Debit Note functionality. To be raised without Fail Pcs. Need to store the cutwastage in wastgae table to avoide the quantity concern. | Done | Sanjeev
11 | i) Quotation By Pass implementation for the Accessory Section which pending from last task. Ii) Hide Residual Shrinkage in fabric POs | Done | Shubhendu
12 | I) Need to show the Rate, GST and Amount in external Challan in fabric and Accessories | Done | Shubhendu
13 | 3) Following details need to be removed from quotation screen a) Best quoted for Ref need to remove b) Quoted Date need to remove c) Remove all the PO Listing d) On quality click show the all last 6 months PO details with supplier details in a pop up. | Done | Shubhendu
14 | Challan issue fixing regarding GST implementation | Done | Shubhendu
15 | Costing Design Update | Done | Dinesh
16 | Working on the Remaining menu pages in IE, IT and HR Creating the Mockup of the costing -- Approved Need to work final now Preparing the Release note -- Keep doing Issue fixing of the different sections. Working on MO Fabric and Accessory section… | Done | Dinesh
17 | Need to work on removal of the Ikandi domain from ERP Analysing with Girish and will proceed after analysis done with discussion | Done | Sanjeev
18 | Menu wise screens issue fixing Bug fixing raised by QA Need to show the Cancel PO as water mark in Cancel PO | Done | Dinesh
19 | Remaining issues need to fix related to current build Working on the inspection screen for showing the serial number Amendment and bug fixing in the lab section -- helped By Sanjeev Need to show Fabric and accessory quality detail in the Debit note of respictive. | Done | Shubhendu On Leave will join on 22 march 2022
20 | Cut issue openning on order confirm Issue request can be done if first stage srv received | Done | Sanjeev
21 | Working on Raise and Revise PO Optimization We will do the Quotation page optimization Issue fixing… Quotation screen open in new tab. Only one accessory po open in po confirmation task by Hemant ji. By the way we are showing the PO in Red color for difference. | Done | Sanjeev
22 | i) Quotation ByPass. If supplier associated with the qualities but not received any quotation then the min default will be shown in the PO screen to select . The style will be faded with the suppliers in dropdown who has not given the quotation. Ii) Need to show the all suppliers with different fonts to segregate the non quoted on raise and revise screen supplier quot pop up too. Issue Fixing | Done | Shubhendu Dinesh (design) On Leave will join on 22 march 2022
23 | Issue Fixing BIPL_ERPMAT-6503 BIPL_ERPMAT-6506 BIPL_ERPMAT-6538 BIPL_ERPMAT-6539 BIPL_ERPMAT-6535 BIPL_ERPMAT-6536 and Others Costing update on last order price and also created history of this Imlementation for penalty on mode change for the mode D(PORT-F)-A/F(CIF) | Done | Sanjeev
24 | Costing design update request from Jeena. Costing should not copy when created version from style in design form | Done | Sanjeev
25 | If opening the manage Fabric PO page from task, then the PO should visible only as search | Done | Sanjeev
26 | Debit note task for marked failed quantity will not be created | Done | Sanjeev
27 | Separate the cut issue report in separate menu. Need to show the challan from the navigation. | Done | Sanjeev
28 | i) Fabric and Accessory section PO Confirmation Task Need to be created to GM Material (Hemant Ji). Ii) This need to be created just after signature done by the Sub ordinates. Handling the task creation and closing of the task. Iii) The implementation for followisng stages of the POs as Defined bellow: Fabric a) Greige -- Done in development b) Dyed -- Done in development c) Print -- Done in development d) Finish -- In Progress e) Rfd -- In Progress f) Embroidery -- In Progress g) Emblishment -- In Progress Accessory -- Pending a) Greige b) Process c) Finish | Done | Sanjeev
29 | i) Implementation of Material Fabric quality search as auto populated. Ii) Need to implement with a separate text box with auto populated iii) This need to be veryfied and modified for Sales Report too… | Done | Sanjeev
30 | i) In All PO ETA must be PO Date + Quotation submitted Days. Ii) And supports | Done | Sanjeev
31 | i) BIPL Price Update from MO for Karan History will be maintained. With Proper Permission ii) Costing Comment should not be copied to new version from style page (Support) | Done | Shubhendu Dinesh (design)
32 | i) Fabric Inspection screen if there are no extra pass quantity or Failed quantity then on QA segnature automatically GM signature must be done. Ii) For Accessory Inspection too same need to be implemented | Done | Shubhendu
33 | i) In Cut issue request need to select the Unit for which the request is made ii) The requested unit need to be visible to the issuer in case of fabric and accessory both iii) Defult unit need to be selected fopr the internal challan screen but this can be changed as well. | Done | Shubhendu
34 | i)Show the Serial Number assoiciated with the fabric and accessory quality in the quotation screen. Ii) This need to sho for internal factory base only need to confirm | Done | Shubhendu
35 | Show the Greige shrinkage in second stage onwards PO for Fabric | Done | Shubhendu
36 | Design Update in following pages i) Costing Page ii) Order Form iii) SRV iv) Raised and Revised Screen Supplier quotation | Done | Dinesh
37 | Few Issues raised for designer i) 6508 -- MO Horizontal Scroll ii) 6509 -- Manage accessory PO fit in whole page iv) 6511 -- Cut issue screen contract number box width and other support design issues | Done | Dinesh
38 | ii) Complete support and Queries related to it Preparing the Fabric summary report and summary Report sql queries | Done | Girish
39 | Sales Report and Core Rewport issue fixing to mach the may 2022 Figures Required qty was coming in negative rectified ETA Date issue fixed | Done | RSB
40 | Name the ShortFall as Layered ShortFall Permission to Accounts team in material module Outhouse PO open from task 1 qty difference in accessory when changing the wastage on ui | Done | RSB and Team
41 | 1) In design page Remarks need to be updated without Postback 2) Show the PO Number and quantity in inspection Page | Done | RSB + Shubhendu
42 | Fixing of SRV allocation after signature Fabric | Done | Ravishankar
43 | SRV issue fixing on 4point check | Done | Ravishankar
44 | Now need to create the queries for accessory Report | Done | Girish
45 | In Fabric PO PDF greige shrinkage visibility for dyed, Print and rfd second stage | Done
46 | Showing the bill no with srv in debit note in Fabric and Accessory | Done
47 | Working on the Modification of the Fabric and accessory PO detail reports as discussed in meeting 1) Totals in Body report should be in Blue colour. 2) In Totals no decimal required. 3) The quality Name need to be separated in Body report as Quality¦ C&C ¦ GSM Use the colours as well. 4) Quantity should be in k and with single decimal. In totals no need of decimals but in k. 5) Value in lack as it is with single decimal and in totals no decimal required. 6) In Detail Body Report show as following Greige Quantity¦ Value 7) In Excels show the Issued Quantity in cutting and balance to issue 8) The top Body Report of summary will have only 3 sections divide in 3 parts having 2 subparts as follows Total active PO With Mill Inhouse Qty Value Qty Value Qty Value This should be independent of type. This will be combined supplier specific. Above points need to be implemented in the current Fabric and accessory reports | Done | Girish and Dinesh
48 | SRV allocation after signature Accessory | Done | Shubhendu & Ravishankar
49 | In Costing now showing all the fabric and accessory unregistered in red color | Done
50 | Various support Reques are in progress | Done
51 | MO implementation | Done | Dinesh
52 | Admin Driven ETA Days implementation for different stages PO 1) Manage group Page Updates i) For fabric Section additional development of the days corresponding to all possible stages. Ii) For Accessory Section additional development of the days corresponding to all possible stages. 2) Changes During the PO Raise on different Stages of fabric and Accessories 3) Updates During the Previous stage first srv Recieving in fabric and accessory both 4) Supplier specific PO summary report with updated ETA information Daily | Done | Shubhendu
53 | Note: Need the editing of days in + only no need to negate the quantity, As discussed in the meeting… For every stage there will be separate + button column The every stage PO will be raised with the admin defined Day based on the stage and quality group. There will be the deviation limit which can be applied too. When the nth stage First SRV received the ETA of the (n+1)th stage po get revised as N Stage First srv Date + (n+1)th stage (PO ETA – PO RaiseDate) No need to shoot any mail automatically in this case a summary report can be shooted supplier specific for all its PO Raised as summery everyday that will serve the purpose. | Done | Shubhendu
54 | Stage show in quotation screen Issue fixing and MO mockups | Done | Dinesh and Shubhendu
55 | 1) In case fabric at the time of stage selection finalisation need to raise the confirm box for auto stock allocation if confirmed as yes then the process will take place otherwise not. | Done
56 | SRV and pass quantity allocation on the planning team preference On high preority Mockup Created and shared | Done
57 | Worked on 1) Website Optimization 2) Fabicon update 3) Collection to Instagram link | Done | Dinesh
58 | Basic MO design Update | Done | Dinesh
59 | Material issue quantity excel | Done | Girish
60 | Costing Pop Up update as mentioned by Sam Sir | Done | Girish
61 | Cut issue screen return quantity need to add in the challan | Done | Girish
62 | Quotation screen Update | Done | Dinesh and Shubhendu
63 | Ikandi website reupdate and Critical Path login enabling | Done | Ravishankar
64 | Quotation Page issue fixing | Done | Ravishankar and Team
65 | Allowing decimal in the SRV receiving | Done | . We will wrap | We must Wrap this by this week any how for release
66 | Accessory Report Updates for the Decimal Implementation | Done | Girish
67 | Need to add the calender on specs upload from where 2 days prior date can be selected by AM as discussed by Karan and team | Done | Girish
68 | 1) Revamping the MO Mockups | Done | Dinesh
69 | 1) In Quotation page GSM, Width and count construction should be in black colour. 2) In Quotation page Style Number also should be black and Serial Number in Blue colour. 3) Decimal Logic need to be changed as follows If quantity < 1000 then full number in case of accessory with decimal too without k Else if quantity >= 1000 and < 10000 then show in k with one decimal place Else always show in k without decimal | Done | Dinesh
70 | Cut issue screen need to work on separate task for Hemant sir and complete revamping | Done | Girish
71 | Now need to store the GST in the Debit note as it need to be updated some time and this should not impact others | Done | Team
72 | Adding year in costing comment | Done | Shubhendu
73 | Restrict cutting entry based on cut issues from material to cutting | Done | Go Ahead from Karan Allocated to Girish
74 | 1) In case fabric and accessory at the time of stage selection finalisation need to raise the confirm box for auto stock allocation if confirmed as yes then the process will take place otherwise not. -- Done 2) Need to ask how much qty want to adjust from stock stage wise 3) By internal SOP the SRV signature need to be done by another team member other than who make entry for double check and SRV allocation will take place on signature done only | Done | RSB
75 | Weighted SAM adding in the Core report | Done | Ravishankar, Dinesh
76 | Hourly Report Update Updated the Daily overhead removed the barrier of 150000 | Done | Ravishankar
77 | Design Changes 1) Direct Repeat in MO will be visible as (DR) in Grey colour. 2) Serial Number would be bold 3) Rate and price font size would be as style number. 4) Description would be italic on MO. 5) Reduce size of stage and po link same as old rate size (the smaller one). 6) In Accessory section the stage and po section need to be moved in the last of the grid. 7) The tooltip grid for fabric and accessory need to remove the Qty and Pcs from title. | Done | Dinesh
78 | Implementation of the Return quantity and remark in external challan | Done | Girish
79 | Daily Update Reports related to the Material as discussed updating the existing reports and amendment 4) Qty to Issue should be renamed as Balance to Issue. 5) Separate the % in a extra column. And provide filter too. Considered Wastage % will be the title 6) We need to remove the shipped styles from the report. 7) Same need to be implemented in the Fabric Report too along with Accessory issuing report. 8) In fabric and accessory mail body will have 1 summary reports in each as given bellow: 9) In both (Fabric / Accessory) summary excel need to show Today quantity. First Report Stock summary Report 1) The Stock summary Report data need to be verify again 2) The report Stock summary and its excel “DetailsFromCutToShip_Excel.xlsx” Renamed as “Production Stock Detail.xlsx” must be moved in the BIPL Core Figures Report. 3) We have to move the Issue – Cut to the first position in grid 4) In Case of Issue – cut we have to use 65% of calculated FOB 5) We have to introduce quantity and value both in the table. 6) Use rupee symbol. 7) We need to add one extra column as Total in end of the grid. 8) In Excel too Pending issue section should be prior to cut section. 9) All the cut sections should be grouped and then stitch section and pack section. Data must be checked. Second Report Daily In/Out summary report 1) Issued section should be renamed as Issue to Cutting 2) In Title add the info about the Value (This is complete value including all stage prices) 3) Fabric_Issued_Quantity.xlsx need to be renamed as Cut Issue Status.xlsx. First sheet will be of same name. The second sheet will be that we develop now for daily srv details. This will be created based on challan only. Name of this sheet would be as Daily Stock Movement.xlsx | Done | Girish
80 | Hi team IT required supplier/processor's address with GST no in INT/EXTS/debit note/credit note. | Done | Girish
81 | In the Raise and revise screen following changes need to be done: 1) We have to remove the bellow columns and have to merge them in the last column a) Qty To Order and Qty to Receive – Remove b) Balance in House --- Remove c) In the last column following will be data as Title – Quantity Breakdown To Order same to Qty To Order To Received (After Shr./ Waste.) same to Qty to Receive with link Stock in House same to Balance in House PO Ordered (send) PO to Receive Pending to Order Actual Shipped but not Issued Shipped and issued Total 2) Need to separate the quality name, GSM, Count construction and width 3) Separate the style number and serial number as in quotation 4) Follow the MO style every where. 5) In Required pop up need to show the serial number, contract number and color print. 6) Apply proper title. 7) Use units every where in short as for meter it should be Mtr. | Done | Girish and Dinesh
82 | Deafult rate and quantity implementation in costing for department specific in costing | Done | Girish and RSB
83 | Daily SRV In and OUT Report (Need to discuss the format to finalise) Excel | Done | Girish
84 | 1) IN MO following changes need to be covered as per suggestion in the todays demo of new release meeting a) Accessory section Colour Print name should be aligned in left. b) MO Width need to be responsive. c) In UI Border duplicity we need to work out. d) Photoshoot Title need to be Gray. e) Order Date need to be in same colour as PO and Stage icon f) Photo shoot date should be in same colour as PO and Stage icon g) The Revenue value besides the BIPL price in bracket should be un bold and same colour as PO and Stage icon h) Accessory name BG colour need to be removed. The size should be reduced as Sam title i) Top Status text and Technical link should be of size as detail j) On Hold text should be in Gray k) For Serial Number ERN 1139 check why Mode dropdown has BG colour is coming. l) Mode text colour should be same as colour as PO and Stage icon | Done | Dinesh
85 | Order History have concern regarding Ex-factory its appearing in different format in the all and also its not visible in the Ex-factory\DC section | Done | Girish
86 | Changes in fabric and accessory Screen 1) Purchase Order and Process Order 2) Show the Invoice number in Inspection screen 3) Production stock detail excel used in the Core figure report the values will come in full not in Crores. 4) In the Production stock summary report the Total will not consider the issued stock now. In the Monthly Costed vs Actual CMT we have to introduce one more column as Stitched FOB just after the Stitched Qty. Value will appear in ₹ and Cr. | Done | Girish
87 | 1) Address in PO and other places we have to manage in 2 lines only. 2) The third option is approved from client side. The Address font should be same as the General Instructions shown in PO. Here the values should be bold but title like GST and Fax etc will be un bold. 3) PO Date and ETA Date should be black and Bold. 4) In the title of Greige shrinkage and Residual shrinkage % sign need to be removed if there are data then show the % with value. 5) Rate should be bold and green and size should be as rupee symbol. 6) The same Header need to be implemented in all POs, Credit Note, Debit Note and Challans etc. 7) Need to wrap all the changes to incorporate in the build upcoming release. 8) The Technical pop up in MO need to be updated as follows: i) Header need to have the following columns and the values will be visible accordingly ii) Technical ¦ ETA ¦ Planned ¦ Actual iii) ETA should be Black and Bold iv) If the Actual is less than or equal to ETA then Green else Red colour. 9) Overhead Column need to be added just after CMT Multiplier in Wastage and CMT Admin. The max range will have least Overhead. As the qty range decreases the Oh Value increases. Validation should be applied that the lesser quantity range will not have less overhead. 10) In every costing when click on the last order price in pop up there will be another grid in bottom with same column only style code will be style numbers. Here for all costing the costing versions latest order price should be shown if order raised. Style should be shown of any shipped , Unshipped order assigned with it. Order by Exfactory desc. | Done | Dinesh and Girish
88 | Table formation for raise and Revise PO screen for all content. | Done | RSB and Dinesh
89 | Sales Report SP Optimization | Done | RSB
90 | Few new points and requirements analyse and added in doc need to finalise after discussion with Hemant ji and SAM sir on Monday | Done
91 | Required Quantity Mock up share The complete dynamic header development of the page | Done | Dinesh & Girish
92 | Address part design Updates 1) Credit Not fabric and accessory 2) Debit Note fabric and accessory 3) Rate size increase in all PO | Done | Dinesh
93 | FOC implementation complete | Done | Girish
94 | Issuing in production from stock the extra quantity | Done | Girish
95 | Few issues and impediments There are approx 6-8 Case need to work | Done | Girish and RSB
96 | Design Impediments and issues approx 3-4 | Done
97 | Raise and Revise PO screen should be open and the default tab based on the first stage of the fabric should be selected. | Done
98 | Search feature in the Manage Production Unit | Done | Girish
99 | Few Admins Optimization In Progress 1) DesignList 2) Print Admin 3) IND Block Admin | Done | Girish
100 | Enhancements in THE UI of the ERP in different sections Creating mock ups for the landing page just after login Design Related issue fixing | Done | Dinesh
101 | 13.1 Different Shades of GST in Accessory | Done | Girish
102 | 13.2 Wastage Admin and costing Update Regarding CMT Change in Costring too | Done | Girish
103 | Is it possible excess fabric to be issued to unit In Cutting Issue screen | Done
104 | 13.3 Accessory combined challan order specific | Done | Girish
105 | Accessory Quantity reallocation refinement and issue fixing | Done | 1 | Girish
106 | 13.4 Stage wise stock summary Report Excel Formats | Done | 2 | Girish
107 | 18.3 The Inhouse % should be as SRV Received / Required Quantity final | Done | 3 | Ravishankar
108 | 18.1 on the "agreed rate" on VA Po, make it a intelligent link which when I click opens up latest 5 rates | Done | 9 | Ravishankar
109 | 15.0 MULTIPLE BILL WITH ONE SRV | Moved in Live | 4 | Girish
110 | 17.0 HSN CODE ASSOCIATION WITH QUALITY AND HAVE TO SHOW IN THE EXTERNAL CHALLAN | Moved in Live | 6 | Rajeev
111 | Now need to update the BIH Pop up by making bellow changes 1) Added one more column Title as Reqd. vs Cut 2) In Issued column also showing the Cut Required 3) Now we have to show the Cut issued % by Cut Required quantity | Moved in Live | 11 | RSB
112 | In 4 point check screen need to show the consumable quantity in bracket with extra quantity | Moved in Live | 13 | RSB, GIRISH
113 | 13.4 Stage wise stock summary Report | Moved in Live | 1 | IT Team with Fabric Team
114 | As discussed the layout of the summary and excel report finalised pending to develop | Already Done
115 | A Daily Report required where for every fabric and accessory stage wise pass quantity and pending quantity to issue to supplier need to be visible. Based on challan issued and previous stage pass quantity received. | Already Done
116 | Need to show the Serial number in inspection screen for fabric and accessory both | Already Done
117 | Need to create a report with the Fabric quality, supplier, Rate and PO as Excel for Core Report | Already Done | 12 | Girish

## Sheet3
Sr No | Tasks
1 | suppliers task to be provided by IT | Communication need to be done by the material team to suppliers and if required sync with IT
2 | imported po to discuss-rates in $ but calculation in rs. | This is on hold for now, We can address this in later stages same as Unit conversion | PO Raise in dollor for visibility purpose only. Quotations too
3 | discount in debit note to be shown in same debit note (like layer short credited by supplier in their inv and rejected fabric returned) | Credit Note can be created against Debit | Credit Note can be created against Debit
4 | required separate task for fabric lost in residual shrinkage | Already done. Task will appear even after cutting after current release | Res shrinkage
5 | how to debit extra charges(rate difference/freight & forwarding) levied by supplier | No issue
6 | R/back(greige) entry from processors/cutting dept(processed any dyed/print/rfd/greige) | We have done for cutting issue not for others | ret
7 | proper allocation of fabric required | We are working on quantity shifting
8 | fabric GM inspection task shows excess fabric due to four point reports after shipment | Need to analyse may be due to manual intervention | Root cause analysis
9 | fabric movement(extn challans/reprocess/rejected)also to be shown in fabric po detail | No issue
10 | IN FABRIC PO DETAIL SHOWING PENDING PO LIKE SDFF3/SDPLF2/SDPLF3 | done
11 | req separate RPOCESS ORDER (FOR JOB WORK)/PURCHASE ORDER ( FOR PURCHASE) | This is on hold for now, We can address this in later stages same as Unit conversion | Process order in other stages than first stgage
12 | mail option for debit note to be provided. | Need to analyse may be due to manual intervention | check mail as per cancle
13 | valuewise fabric stock & party account required | We have done for cutting issue not for others
14 | wrong rate picked in greige issue challan & GST amt must be visible. | We are working on quantity shifting Need to show in segregation | need detail
15 | no of thans/bales in srv | Need to discuss
16 | decimal point to be provided for qty recd & issued
17 | req separate task for sample fabric | Need to discuss
18 | required report for internal challan issued to unit | Need to discuss
19 | is it possible excess fabric to be issued to unit | Stock allocation in production
20 | in fabric issue request task freeze before fabric issue (completion) | Already done. Task will appear even after cutting after current release
| For Corogated Boxes and other accessory department specific avg and rate use | To Do | Pending with Karan to finalise
Daily In and Out report for the inventory
| GST Number in External Challan | Requirement from Vinay Fabric
| New Report of the finishing superwiser need to created need to add data in the qc pop up |  | Padam

## Sheet4
Quality | Supply Type | Global stock |  | With Processor |  | SRV In In Checking |  | Pending to Issue |  | Issued but not cut |  | Failed Stock
|  | Qty | Value | Qty | Value | Qty | Value | Qty | Value | Qty | Value | Qty | Value
Xyz | Greige
Dyed
Print
RFD 1st Stage
RFD 2nd Stage
Embroidery
Emblishment
Finish
First stage Value |  | Total inhouse stock value including global stock, in process or in checking
Secondstage Value |  | Total inhouse stock value including global stock, in process or in checking This include the corresponding value of the previous stages too.
First stage Value |  | Total inhouse stock value including global stock, in process or in checking This include the corresponding value of the previous stages too.
First stage Value |  | Total inhouse stock value including global stock, in process or in checking This include the corresponding value of the previous stages too.
| Serial Number | Contract Number | Quantity | Thread Quality | Colour Print | Current Thread Average | Edit Thread Average | Apply to all
| ASO 5232 | CN12343 | 5000 | Thread Spun Poly Tkt100 5K M 3ply | Black | 2.5 |  | ChkBox
|  | CN12344 | 10000 | Thread Spun Poly Tkt100 5K M 3ply | Blue | 3 |  | ChkBox
|  | CN12345 | 2500 | Thread Spun Poly Tkt100 5K M 2ply | Black | 1.2 |  | ChkBox
|  | CN12346 | 3100 | Thread Spun Poly Tkt100 5K M 2ply | Blue | 0.8 |  | ChkBox
2.5
3
1.4
0.6